## Slide 1: Joint informational hearing Senate Transportation Committee & Senate Budget Sub-committee #2
Lenny Mendonca, CHSRA Board Chairman
Brian Annis, Secretary, California Transportation Agency
March 26, 2019

## Slide 2
Credibility:
The quality of being believable and worthy of trust.
Senate joint informational hearing California high-speed rail authority

## Slide 3
Re-establishing Credibility through:
  Transparency
  Keeping Our Commitments
  Delivering High-Speed Rail trains while ‘living within our means’
Senate joint informational hearing California high-speed rail authority

## Slide 4
Governor Newsom is for delivering high-speed rail for Californians in a way that is:
Transparent
Responsible
Realistic
Accountable
Senate joint informational hearing California high-speed rail authority

## Slide 5
“High-speed rail is much more than a train project. It’s about economic transformation and unlocking the enormous potential of the Valley.”
- Governor Newsom
Senate joint informational hearing California high-speed rail authority

## Slide 6
Board of Director’s Finance and Audit Committee
  Public Meetings
  Reviews and monitors project status, trends, challenges and opportunities in public forum
  Committee documents/monthly reports are available online today
TRANSPARENCY – BOARD OF DIRECTORS
Senate joint informational hearing California high-speed rail authority

## Slide 7
TRANSPARENCY – 2018 BUSINESS PLAN
First plan to assign dollars and time to risks
First plan that used ranges to estimate costs
Recognized funding constraints and introduced the idea of delivering the project in “building blocks,” like most major infrastructure projects are delivered
Senate joint informational hearing California high-speed rail authority

## Slide 8
TRANSPARENCY – 2018 BUSINESS PLAN
Set the following priorities:
  Meet our commitments to the federal government
  Complete Central Valley Segment
  Complete Environmental Reviews Systemwide
  Add Central Valley Track and Systems
  Extend Central Valley Segment from orchard into downtown Bakersfield
Senate joint informational hearing California high-speed rail authority

## Slide 9
TRANSPARENCY – 2018 BUSINESS PLAN
Set the following priorities
  Explore and Report Options for Early Interim Service in the 2019 Project Update Report (PUR)
  Subject cost estimates to further review and risk analysis and report in the PUR
  Invest Remaining “Bookend” Funds
  Pursue additional funding or financing to complete full system
Senate joint informational hearing California high-speed rail authority

## Slide 10
TRANSPARENCY – NEW MEASURES
Governor Newsom: Make project change orders available to the public online.
      Status: 338 change orders now available on our “Transparency and Accountability” page at the Authority’s website.
State Auditor: Provide quarterly reporting to the Legislature on our progress toward meeting our federal Funding Agreement requirements.
      Status: First report provided January 30, 2019, the next one due on April 30, 2019.
Senate joint informational hearing California high-speed rail authority
10

## Slide 11
“We will continue our regional projects in the north and south.”
- Governor Newsom
Senate joint informational hearing California high-speed rail authority

## Slide 12
Northern California:
  Caltrain Electrification - $600m bond funds plus $113m in Cap and Trade funds
Senate joint informational hearing California high-speed rail authority
KEEPING OUR COMMITMENTS

## Slide 13
  Southern California:
  Rosecrans/Marquardt Grade Separation ($77m)
LA Union Station improvements ($423m)
Senate joint informational hearing California high-speed rail authority
KEEPING OUR COMMITMENTS

## Slide 14
“We will finish Phase 1 (San Francisco – Los Angeles /Anaheim) environmental work.” – Governor Newsom
Progressing all environmental work
Requested streamlining authority from federal government
Environmental work is on schedule to be completed by the required date in the federal funding agreement (2022)
Senate joint informational hearing California high-speed rail authority
KEEPING OUR COMMITMENTS

## Slide 15
KEEPING OUR COMMITMENTS
Completing environmental work is necessary in front of future construction contracts – necessary to:
      Refine cost estimates
      Advance design
      Identify and mitigate risk
      Develop strategies for project development work (i.e., ROW acquisition, utility relocations, etc.)
      Ready shared corridors for investments as funding opportunities become available
Senate joint informational hearing California high-speed rail authority

## Slide 16
DELIVERING HSR WHILE LIVING WITHIN OUR MEANS
Project does not have all the funding needed to complete the entire project statewide……and it never has:
  2008: Bond Measure (Proposition 1A) passes and provides 20% of the project’s then estimated costs.
  2018: With a stable Cap and Trade program through 2030, federal funds and Proposition 1A funding, the Authority has access to just under 30% of today’s estimated project costs
Senate joint informational hearing California high-speed rail authority

## Slide 17
DELIVERING HSR WHILE LIVING WITHIN OUR MEANS
How do we make high-speed rail real in California within the reasonable estimate of funding available to the project today?
  2017: The Authority contracted with an Early Train Operator (DB who operates high-speed rail in Germany) to advise on operational issues for service in California;
  2018: Business Plan directs the ETO to analyze and make recommendations for early interim service that make the most sense.
  2018: Early indication is that Merced-Fresno-Bakersfield is the only early service line that makes sense in the Central Valley—the only place in the state the environmental work is complete or near completion and construction is underway.
Senate joint informational hearing California high-speed rail authority

## Slide 18
DELIVERING HSR WHILE LIVING WITHIN OUR MEANS
Merced-Fresno-Bakersfield line has the benefit of offering a 171-mile high-speed service connecting three of the fastest growing counties in California (Merced, Fresno, Kern).
Bakersfield
Kings/Tulare
Fresno
Madera
Merced
171 Miles
Merced to Bakersfield
Senate joint informational hearing California high-speed rail authority
18

## Slide 19
DELIVERING HSR WHILE LIVING WITHIN OUR MEANS
The service would provide important connections to ACE service traveling to San Jose and Amtrak service traveling to Sacramento and Oakland, while reducing travel times between 90 and 100 minutes through the Central Valley.
Senate joint informational hearing California high-speed rail authority
19

## Slide 20
DELIVERING HSR WHILE LIVING WITHIN OUR MEANS
On May 1, 2019, the Authority, will release a Project Update Report to the Legislature outlining the ETO analysis for early operations, benefits, risks, costs and schedule, as well as an implementation plan.
Senate joint informational hearing California high-speed rail authority
20

## Slide 21: Overarching strategy Applying lessons learned in the central valley
Third Parties: Reset Relationships
  Reinstitute Master Agreement Terms & Conditions
  Define and finalize requirements & scope
  Actively engage in consultation and design reviews
Design Builder (DB) Completes Designs
  Defines project footprint for right of way acquisition and environmental clearance
  Predecessor to construction
Right of Way (ROW) & Environmental
  ROW: Define - Map - Acquire
  Environmental clearance
Holistic Program Approach
Integrated Risk Management & Mitigation
Engaged Contract Management
Transparency & Accountability through Governance

## Slide 22: Program approach critical actions
Action | Result
Increased presence of Chief and Deputy Chief Operating Officers in the Central Valley | North to South review of alignments to verify “Get-to-Work” Schedules Improved dialogue through monthly meetings with DB Executives
Dedicated “Strike Team” to focus Authority effort in the Central Valley | Resolve multiple-year “legacy” issues Increase collaboration with Project and Construction Manager (PCM) Resolve issues and open worksites for DB Contractors Increased PCM guidance
Separated Contract Operations from Commercial Oversight for more efficient execution | Improved capacity for commercial oversight Increased ability to manage contract performance
Optimizing staff & making additional critical hires | Increase in State contract management staff Develop staff through Design-Build contract training
Improved Construction Package project controls | Increased accountability and enhancing performance

## Slide 23: CONSTRUCTION PACKAGE 1 JANUARY 2019
AVENUE 15
AVENUE 12
AVENUE 11
AVENUE 8
FRESNO TRENCH
TUOLUMNE STREET BRIDGE
MUSCAT AVE
SAN JOAQUIN RIVER VIADUCT
AMERICAN AVENUE
CEDAR VIADUCT
COTTONWOOD CREEK
FRESNO RIVER VIADUCT
ROAD 27
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
On Hold for Utility Relocation
99 REALIGNMENT
Total Guideway Miles: 25 |  |  | 
 | Jan |  | 
In Progress | 7.25 |  | 
Completed | 0 |  | 
Total | 7.25 |  | 
Total Structures: 31 |  |  | 
 | Jan |  | 
In Progress | 7 |  | 
Completed | 4 |  | 
Total | 11 |  | 

## Slide 24: CONSTRUCTION PACKAGE 1 December 2019
FRESNO RIVER VIADUCT
AVENUE 15
AVENUE 12
AVENUE 11
AVENUE 8
AVENUE 7
99 REALIGNMENT
TUOLUMNE STREET BRIDGE
ROAD 27
SAN JOAQUIN RIVER VIADUCT
AVENUE 15 1/2
GOLDEN STATE BLVD
MCKINLEY AVENUE
COTTONWOOD CREEK
MUSCAT AVE
AMERICAN AVENUE
CEDAR VIADUCT
HERNDON AVE
FRESNO TRENCH
BELMONT AVENUE
AVENUE 10
AVENUE 9
Total Guideway Miles: 25 |  |  | 
 | Jan | Jun | Dec
In Progress | 7.25 | 12 | 18.5
Completed | 0 | 0 | 0
Total | 7.25 | 12 | 18.5
Total Structures: 31 |  |  | 
 | Jan | Jun | Dec
In Progress | 7 | 9 | 10
Completed | 4 | 6 | 10
Total | 11 | 15 | 20
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
On Hold for Utility Relocation

## Slide 25: CONSTRUCTION PACKAGE 2-3 January 2019
CORCORAN HWY
KANSAS AVE
KENT AVE
EXCELSIOR AVE
DAVIS AVE
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
Total Guideway Miles: 65 |  |  | 
 | Jan |  | 
In Progress | 21 |  | 
Completed | 12 |  | 
Total | 33 |  | 
Total Structures: 50 |  |  | 
 | Jan |  | 
In Progress | 3 |  | 
Completed | 0 |  | 
Total | 3 |  | 

## Slide 26: CONSTRUCTION PACKAGE 2-3 DECEMBER 2019
CORCORAN HWY
KANSAS AVE
KENT AVE
EXCELSIOR AVE
DAVIS AVE
LINCOLN AVE
SOUTH AVE
CANEJO AVE
ADAMS AVE
MOUNTAIN VIEW AVE
FLINT AVE
FARGO AVE
AVE 88
IDAHO AVE
JACKSON AVE
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
PEACH AVE
Total Guideway Miles: 65 |  |  | 
 | Jan | Jun | Dec
In Progress | 21 | 23 | 28
Completed | 12 | 22 | 37
Total | 33 | 45 | 65
Total Structures: 50 |  |  | 
 | Jan | Jun | Dec
In Progress | 3 | 7 | 14
Completed | 0 | 0 | 4
Total | 3 | 7 | 18

## Slide 27: CONSTRUCTION PACKAGE 4 January 2019
GARCES HWY
POND ROAD
WASCO VIADUCT
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
Total Guideway Miles: 21 |  |  | 
 | Jan |  | 
In Progress | 11 |  | 
Completed | 0 |  | 
Total | 11 |  | 
Total Structures: 11 |  |  | 
 | Jan |  | 
In Progress | 3 |  | 
Completed | 0 |  | 
Total | 3 |  | 

## Slide 28: CONSTRUCTION PACKAGE 4 December 2019
GARCES HWY
POND ROAD
POSO CREEK
MCCOMBS AVE
STATE ROUTE 46
POSO AVENUE
PEDESTRIAN UP
WASCO VIADUCT
KIMBERLINA ROAD
PETERSON ROAD
MERCED AVE
Not Cleared for Construction
Construction in Progress
Projected Construction Completion
Total Guideway Miles: 21 |  |  | 
 | Jan | Jun | Dec
In Progress | 11 | 17 | 11
Completed | 0 | 0 | 10
Total | 11 | 17 | 21
Total Structures: 11 |  |  | 
 | Jan | Jun | Dec
In Progress | 3 | 6 | 7
Completed | 0 | 0 | 4
Total | 3 | 6 | 11

## Slide 29
RESPONSE TO STATE AUDITOR
  Authority welcomed the audit and took its recommendations very seriously
  Findings and recommendations built on issues we had identified in 2018 Business Plan
  Committed to open dialogue and addressing all of the Auditor’s recommendations on the schedule
Senate joint informational hearing California high-speed rail authority

## Slide 30
FEDERAL RAILROAD ADMINISTRATION (FRA) GRANT AGREEMENT
February 19th – FRA sent letter threatening to de-obligate $929 million in federal FY 10 funds.
March 4th – Authority sent two letters in response, specifically:
Project continues to further purpose for which federal funds were obligated;
We are making steady progress toward meeting grant requirements;
Noted that FRA has taken actions detrimental to timely progress on environmental reviews;
Inviting FRA Administrator to help re-establish functional relationship between Authority and the FRA.
Senate joint informational hearing California high-speed rail authority

## Slide 31: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
Direct Investment
Total Authority Expenditures that drive the Economic Output
JULY 2006
JUNE 2018
$4.8 Billion
$4.8 Billion from July 2006 through June 2017
95% Went to California Firms and Workers

## Slide 32: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
California State Wide Economic Impacts
2006 - 2018
JOB-YEARS OF
EMPLOYMENT
37,600 – 42,600
Job Years - Job-Years are the equivalent number of one-year-long, full-time jobs supported by the project.

## Slide 33: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
California State Wide Economic Impacts
2006 - 2018
$2.60 - $2.99 BILLION
LABOR INCOME
Labor income includes all forms of employment income, including compensation (wages, benefits, and payroll taxes) firms paid to employees, and income earned by self-employed workers or unincorporated sole proprietorships.

## Slide 34: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
$6.8 - $7.6
Billion
ECONOMIC OUTPUT
Economic Output - Economic output represents the total contribution the Program has made to the Gross Domestic Product (GDP) in California and the US or the economic “value-add”.
California State Wide Economic Impacts
2006 - 2018

## Slide 35: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
54%
of project expenditures occurred in designated disadvantaged communities throughout California, spurring economic activity in these areas.
Direct Investments
2006 - 2018

## Slide 36: 2018 Economic Impact Report CALIFORNIA HIGH-SPEED RAIL AUTHORITY
Direct Investment in Small Businesses
2006 - 2018
488
Small Businesses are either committed, utilized or actively working on the project
The Authority has a 30% Small Business Participation goal including:
10% Disadvantaged Business Enterprises (DBE) participation
3% Disabled Veteran Business Enterprises (DVBE) participation

## Slide 37
IMPLEMENTATION STRATEGY SUMMARY
Deliver High-Speed Rail in California by:
Getting trains on the ground ASAP in the Central Valley, where the environmental work is near completion and construction is underway;
Completing the environmental work statewide by 2022;
Completing our “bookend” commitments in northern and southern California;
Being prepared to expand the system, consistent with Proposition 1A, as federal and/or private funding opportunities materialize.
Senate Joint informational hearing California high-speed rail authority

## Slide 38
APPROACH TO DELIVERY SUMMARY
We are working to get high-speed rail operational in California by:
Being transparent on opportunities and challenges;
Maintaining our Commitments to our partners;
Delivering High-Speed Rail while ‘living within our means.’
Senate joint informational hearing California high-speed rail authority

## Slide 39
Lenny Mendonca, Board Chairman
(916) 322-0694 lenny.mendonca@gobiz.ca.gov
Brian Annis, Secretary
California Transportation Agency
(916) 323-5401 brian.annis@calsta.ca.gov
Headquarters California High-Speed Rail Authority 770 L Street, Suite 800 Sacramento, CA 95814 www.hsr.ca.gov
instagram.com/cahsra
facebook.com/CaliforniaHighSpeedRail
twitter.com/cahsra
youtube.com/user/CAHighSpeedRail
SenatE joint informational hearing California high-speed rail authority